**Chapter 270: Uniform Reporting System for Quality Data Sets**

*(Major Substantive) 07/05/2018*

***Proposed Rulemaking Timeline:***

* 06/07/2018 MHDO Board **approves** **initiating rulemaking**
* 06/29/2018 Draft of proposed rule changes and summary of changes sent to Karynlee

for review.

* 07/06/2018 Karynlee will send draft of proposed rule and summary of changes to

the Maine Hospital Association.

* 07/17/2018 Karynlee will send draft of proposed rule and summary of changes, &

MAPA forms to **AG for preliminary review** & the Governor’s Office.

* 08/07/2018 MAPA forms sent to Secretary of State’s Office for publication
* 08/15/2018 Newspaper publication date
* 09/06/2018 Public Hearing

* 09/17/2018 Deadline for public comments (10 days from public hearing, 5 p.m.)
* \_\_\_\_\_\_\_\_\_ Review of *provisional adoption* of the rule changes by AG’s Office
* *\_\_\_\_\_\_\_\_\_ Approval by the Governor’s Office of changes made in the proposed rule due to public comments* ***(if none, this step can be skipped)***
* 12/06/2018 MHDO Board approves ***provisional adoption*** of rule changes

(*Board must adopt 150 days from comment period deadline)*

* \_\_\_\_\_\_\_\_\_\_ *Provisional Adoption* package sent to the Secretary of State’s

Office & Legislative Committee (*legislative resolve, must submitted to the Legislative Committee for review by the 2nd Friday of the new year* ***01/11/2019)***

* \_\_\_\_\_\_\_\_\_\_ Legislative Committee Review (public hearing & work session)
* \_\_\_\_\_\_\_\_\_\_ ***Final Adoption*** of Major Substantive Rule by MHDO Board
* \_\_\_\_\_\_\_\_\_\_ Final review of final adoption of the rule changes to the AG’s Office
* \_\_\_\_\_\_\_\_\_\_ Send adoption package to the SOS for final adoption