**MHDO General Operations Status – March 6, 2014**

|  |  |  |
| --- | --- | --- |
| Project is in critical status. Factors beyond MHDO regulatory control effect project delivery schedule. | Project is underway. MHDO (and partners, where appropriate) has developed work plan to process backlog and return to normal data schedule.  | Project is up to date and operating under normal data schedule. |

| **Status** | **Project** | **Project Component** | **Backlog** | **Estimated Release****Date** | **Notes** |
| --- | --- | --- | --- | --- | --- |
|  |  | Hospital Encounter Data | Inpatient | CY2012CY2013 |  | Q4 2013 data due to MHDO April 1. CY2013 data is scheduled to be released July 2014 |
|   | Hospital Encounter Data | Outpatient | CY2012CY2013 |  | Same schedule as inpatient data |
|  |  |  |  | All Payer Claims (APCD) | Commercial-Q42013Medicaid- Q42013 | N/AN/A | April 1, 2014 |  |
|  |  |
|  | All Payer Claims (APCD) | Medicare CY2012First two quarters of 2013 | N/A | April 1, 2014not  |  |
|   | HealthCost Web Site(Price Transparency – Commercial and Uninsured) |  | 20122011 | Both 2011 and 2012 data has been reviewed externally and are now Included in HealthCost. | Working on interim release which includes data for the time period July 1, 2012 to June 30, 2013. |
| Current – 2011 available on site | Hospital Financial Data |  | NA | February 2014 | 2012 Hospital financial templates are now available. Working on developing the standard financial  |
| MONAHRQ 4.1 software available end of April. Will update using new version. | MONAHRQ |  | 20112012 | Revised date: Q12014 | MONAHRQ uses local hospital discharge data andincludes selected measures from the CMS “Hospital Compare” website including Mortality, Readmissions, Process of Care, and HCAHPS survey of patients’ experiences to allow States to create local healthcare reporting websites.Based on Inpatient Hospital Encounter data.Version 5.0 available in 2014 – allows for multi-year comparisons. Will work with HSRI to incorporate into Web Portal. Plan is to run 2012 data through v. 5.0 |